## WBS
TASK ID | ACTIVITY | MANDAYS | START | END | ACTUAL | BUDGET | COST | STATUS | PM | D | U | TOTAL
1 | Integrated Hotel Management System
1.1 | Initiation Phase
1.1.1 | Information Gathering | 0.5 | 01/22/2024 | 01/22/2024 | 01/22/2024 | 1500 | 1000 | COMPLETE | 1000 |  |  | 1000
1.1.2 | Problem Identification | 0.125 | 01/22/2024 | 01/22/2024 | 01/22/2024 | 375 | 250 | COMPLETE | 250 |  |  | 250
1.1.3 | Project Goal Setting | 0.125 | 01/22/2024 | 01/22/2024 | 01/22/2024 | 375 | 250 | COMPLETE | 250 |  |  | 250
[9 empty] | 1500 | 0 | 0 | 1500
1.2 | Definition Phase
1.2.1 | Creating Project System Model | 0.25 | 01/28/2024 | 2024-02-02 | 01/28/2024 | 1300 | 875 | COMPLETE | 500 | 375 |  | 875
1.2.2 | Developing Project Methodology and Strategies | 0.25 | 01/29/2024 | 2024-02-02 | 01/29/2024 | 1300 | 875 | COMPLETE | 500 | 375 |  | 875
1.2.3 | Creating a WBS | 0.25 | 01/30/2024 | 2024-02-02 | 01/30/2024 | 750 | 500 | COMPLETE | 500 |  |  | 500
1.2.4 | Defining Project Team | 0.25 | 2024-01-02 | 2024-02-02 | 2024-01-02 | 750 | 500 | COMPLETE | 500 |  |  | 500
[9 empty] | 2000 | 750 | 0 | 2750
1.3 | Execution Phase
1.3.1 | Designing Hotel Management System | 1 | 2024-02-02 | 2024-01-03 | 2024-05-02 | 5250 | 3500 | COMPLETE | 2000 | 1500 |  | 3500
1.3.2 | Developing Prototyping | 2 | 2024-09-02 | 2024-01-03 | 02/26/2024 | 10500 | 7000 | COMPLETE | 4000 | 3000 |  | 7000
1.3.3 | Testing Prototype | 0.5 | 2024-12-02 | 2024-01-03 | 02/27/2024 | 3000 | 2000 | COMPLETE | 1000 | 750 | 250 | 2000
1.3.4 | Gather Feedback and Update Prototype | 0.75 | 2024-12-02 | 2024-01-03 | 02/28/2024 | 4500 | 3000 | COMPLETE | 1500 | 1125 | 375 | 3000
1.3.5 | Develop System | 2 | 2024-12-02 | 2024-01-03 | 02/29/2024 | 10500 | 7000 | COMPLETE | 4000 | 3000 |  | 7000
1.3.6 | Final System Testing | 0.25 | 02/23/2024 | 2024-01-03 | 02/29/2024 | 1500 | 1000 | COMPLETE | 500 | 375 | 125 | 1000
1.3.7 | Deployment | 0.5 | 02/27/2024 | 2024-01-03 | 2024-01-03 | 2500 | 1750 | COMPLETE | 1000 | 750 |  | 1750
[9 empty] | 14000 | 10500 | 750 | 25250
1.4 | Control Phase
1.4.1 | Maintenance | 0.5 | 2024-03-03 | 2024-08-03 | 2024-06-03 | 2500 | 1750 | COMPLETE | 1000 | 750 |  | 1750
1.4.2 | Project Status Meetings | 0.25 | 2024-05-03 | 2024-08-03 | 2024-07-03 | 1300 | 875 | COMPLETE | 500 | 375 |  | 875
1.4.3 | Project Management | 0.25 | 2024-06-03 | 2024-08-03 | 2024-08-03 | 1300 | 875 | COMPLETE | 500 | 375 |  | 875
[9 empty] | 2000 | 1500 | 0 | 3500
1.5 | Close Out Phase
1.5.1 | Document Lessons Learned | 0.25 | 2024-10-03 | 03/15/2024 | 03/13/2024 | 1300 | 875 | COMPLETE | 500 | 375 |  | 875
1.5.2 | Gain Formal Acceptance | 0.25 | 2024-11-03 | 03/15/2024 | 03/14/2024 | 1300 | 875 | COMPLETE | 500 | 375 |  | 875
[9 empty] | 1000 | 750 | 0 | 1750

## RATE PER ROLE
ROLES | DESCRIPTION | RATE/DAY (PHP)
PM | Project Manager | 2000
D | Developer | 1500
U | User | 500

## BUDGET
BUDGET PER PHASE
PHASE | BUDGET
Initiation Phase | 2250
Definition Phase | 4100
Execution Phase | 37750
Control Phase | 5100
Close out Phase | 2600
TOTAL | 51800

## COST
COST PER PHASE
PHASE | COST
Initiation Phase | 1500
Definition Phase | 2750
Execution Phase | 25250
Control Phase | 3500
Close out Phase | 1750
TOTAL | 34750